## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Introduction to project | MUST HAVE | No Dependency | Anakala Harshitha | 3- Completed
S1 | S1 | US-001 | Project setup and environment configuration | MUST HAVE | Python, VS Code | Anakala Harshitha | 3- Completed
S2 | S2 | US-001 | Design system archtecture | MUST HAVE | FastAPI,Streamlit | Anakala Harshitha | 3- Completed
S2 | S2 | US-001 | Implement nmap based vulnerability scanner | MUST HAVE | Nmap | Anakala Harshitha | 3- Completed
S3 | S3 | US-001 | Integrate threat intelligence API(Virustotal) | MUST HAVE | Virustotal API | Anakala Harshitha | 3- Completed
S4 | S4 | US-001 | Develop risk score engine | MUST HAVE | Python Logic | Anakala Harshitha | 3- Completed
S5 | S5 | US-001 | Database integration for scan storage | MUST HAVE | SQLite | Anakala Harshitha | 3- Completed
S6 | S6 | US-001 | Build interactive Dashboard | MUST HAVE | Streamlit | Anakala Harshitha | 2- In Progress
S7 | S7 | US-001 | Implementing scan history tracking and email eport generation feature | SHOULD HAVE | Database | Anakala Harshitha | 2- In Progress
S8 | S8 | US-001 | Final testing and deployment | MUST HAVE | Streamlit | Anakala Harshitha | 2- In Progress
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 69 | 19 | 12 | 10 | 8 | 6 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction to project | 2026-02-04 | 2026-02-06 | Anakala Harshitha | Others | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Project setup and environment configuration | 2026-02-07 | 2026-02-08 | Anakala Harshitha | Design | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Design system archtecture | 2026-02-11 | 2026-02-11 | Anakala Harshitha | Coding | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-03 | Implement nmap based vulnerability scanner | 2024-02-12 | 2026-02-15 | Anakala Harshitha | Coding | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-04 | Integrate threat intelligence API(Virustotal) | 2026-02-16 | 2026-02-22 | Anakala Harshitha | Coding | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-05 | Develop risk score engine | 2026-02-23 | 29-02-2026 | Anakala Harshitha | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-06 | Database integration for scan storage | 2026-03-02 | 2026-03-06 | Anakala Harshitha | Backend | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-07 | Build interactive Dashboard | 2026-03-09 | 2026-03-13 | Anakala Harshitha | Frontend | 2- In Progress | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-08 | Implementing scan history tracking and email eport generation feature | 2026-03-16 | 2026-03-20 | Anakala Harshitha | Integration Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 1900-01-09 | Final testing and deployment | 2026-03-23 | 2026-03-27 | Anakala Harshitha | Testing | 2- In Progress | 2 | Day 1: 0; Day 2: 0; Day 3: 0; Day 4: 0; Day 5: 0; Day 6: 1; Day 7: 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Difficulty setting up development environment | Installed required dependencies and configured environment
Sprint 1 | Day 4 | Confusion in system architecture design | Conducted team discussion and finalized architecture
Sprint 2 | Day 7 | Issues running Nmap in Python | Debugged using subprocess and tested commands
Sprint 2 | Day 9 | API integration errors (VirusTotal) | Verified API keys and fixed request handling
Sprint 2 | Day 12 | Risk scoring logic unclear | Designed scoring formula and tested scenarios
Sprint 3 | Cat 15 | Database connection errors | Fixed SQLite connection and schema issues
Sprint 4 | Day 18 | Dashboard UI not rendering properly | Debugged Streamlit layout and components
Sprint 5 | Day 20 | Difficulty storing scan history | Optimized database queries
Sprint 6 | Day 23 | Email integration issues | Configured SMTP and tested mail sending
Sprint 7 | Day 26 | Deployment issues | Fixed server configuration and tested deployment
¦ Sprint Day ¦ Impediments ¦ Action Taken ¦

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-02-04 | 2026-02-06 | Anakala Harshitha | Testing APIs and features regularly | Hardcoding values in code | Documenting implementation
2 | Sprint 3 | 2026-02-16 | 2026-02-22 | Anakala Harshitha | Prioritizing Python practice | Delaying integration of modules | Learning new tools and technologies
3 | Sprint 4 | 2026-02-23 | 29/02/2026 | Anakala Harshitha | Optimizing database queries | Skipping input validation | Maintaining consistent workflow
4 | sprint 5 | 2026-03-02 | 2026-03-06 | Anakala Harshitha | Following Agile practices strictly | Poor time management | Conducting regular self-review (stand-ups)